## Sheet1
JYOTHY INSTITUTE OF TECHNOLOGY
PROJECT WORK BREAK DOWN STRUTCTURE
PROJECT TITLE : PATH FINDER
DATE : | ARJUN H N | KARTHIK KUMAR H | VARUN K MURTHY
MILESTONE 1 : DISCUSSING ABOUT PROJECT TITLE
2016-10-02 | Preparing WBS | Preparing WBS | Preparing WBS
2016-10-03 |  | Preparing SRS | Preparing SRS
2016-10-04
2016-10-05 | Submission of SRS and WBS
2016-10-06 | INTERNALS
2016-10-07
2016-10-08
2016-10-09 | SUNDAY
2016-10-10 | Pre-processor Directives | Arrays & Strings | Memory
2016-10-11
2016-10-12
2016-10-13 | Preprocessor conditionals | Pointers | Dynamic Memory Allocation
2016-10-14
2016-10-15
2016-10-16 | Pointer – Memory Allocation Pointer – Declaration & Initialization | Structures – The Definition Structures – Declaration & Type | Memory Organization Code Segment
2016-10-17 | Pointer – Declaration & Initialization | Structures – Declaration & Type | Code Segment
2016-10-18
2016-10-19
2016-10-20 | Pointers dereferencing | Pointers to structs | Arrays
2016-10-21
2016-10-22
2016-10-23 | Bitwise Operations Logical Operators – Short Circuit | File Access File Access Modes | Standard I/O Library Files & Streams
2016-10-24
2016-10-25
2016-10-26 | Storage Classes | Automatic Variables and Stack | Return Values and Error Values
2016-10-27 | Storage Class Specifiers | Static Variables and Functions | Character Based File I/O
2016-10-28 | Scope of a Variable | True meaning of Extern | Line Based File I/O
2016-10-29 | ASSIGNMENT
2016-10-30 | ASSIGNMENT1 : A program to generate subsets of{0,1,2,3,4} | ASSIGNMENT 2 : A program to check if a point (x,y)is on straightline | ASSIGNMENT3 : program to print all permutation of your name
2016-10-31
2016-11-01 | fast ip routing | finding the best path between nodes | conjection control in a network
2016-11-02
2016-11-03
2016-11-04 | calculation of optimal route | finding the IP address | listing out the different types of topologies possible for our network
2016-11-05
2016-11-06
2016-11-07
2016-11-08 | LAB INTERNALS
2016-11-09
2016-11-10
2016-11-11
2016-11-12
2016-11-13
2016-11-14 | THIRD INTERNALS
2016-11-15
2016-11-16
2016-11-17 | FINAL EXTERNAL EXAMS
2016-11-18
2016-11-19
2016-11-20
2016-11-21
2016-11-22
2016-11-23
2016-11-24
2016-11-25
2016-11-26
2016-11-27
2016-11-28
2016-11-29
2016-11-30
2016-12-01
2016-12-02
2016-12-03
2016-12-04
2016-12-05
2016-12-06
2016-12-07
2016-12-08
2016-12-09
2016-12-10
2016-12-11
2016-12-12
2016-12-13
2016-12-14
2016-12-15
2016-12-16
2016-12-17
2016-12-18
2016-12-19
2016-12-20
2016-12-21
2016-12-22
2016-12-23
2016-12-24
2016-12-25
2016-12-26
2016-12-27
2016-12-28
2016-12-29
2016-12-30
2016-12-31
2017-01-01 | MILESTONE 2 : ANALYSIS OF EXISTING ALGORITHMS AND IMPLEMENTING
2017-01-02 | Analysis of corrective and perventive methods for our project | Debugging the errors in the code | Identifiying The nodes
2017-01-03
2017-01-04
2017-01-05
2017-01-06
2017-01-07 |  |  | Analysing the mac and IP address of nodes
2017-01-08
2017-01-09
2017-01-10 |  | Writing the code for mesh topology
2017-01-11 | Analysis the failures (link or node or packet overflow)
2017-01-12 |  |  | setting the attribute to the network
2017-01-13
2017-01-14
2017-01-15
2017-01-16
2017-01-17
2017-01-18
2017-01-19 | Sequencing the packets in node level
2017-01-20
2017-01-21 |  |  | Generating base stations for the network and point of contact
2017-01-22 |  | Reducing the cost decision
2017-01-23
2017-01-24
2017-01-25
2017-01-26
2017-01-27
2017-01-28
2017-01-29
2017-01-30 | Conjection control in a network
2017-01-31
2017-02-01 |  | Finalizing the optimal route between the nodes | listing out the different types of topologies possible for our network
2017-02-02
2017-02-03
2017-02-04
2017-02-05
2017-02-06
2017-02-07
2017-02-08
2017-02-09 | Writing the code for bus topology
2017-02-10 |  | Calculation of optimal route
2017-02-11 |  |  | Coding for star and ring topology
2017-02-12
2017-02-13
2017-02-14
2017-02-15 | Combining and Compiling the code
2017-02-16
2017-02-17 |  | Debugging the errors in the code | performing number of iterations for different topologies
2017-02-18
2017-02-19
2017-02-20
2017-02-21
2017-02-22
2017-02-23 | Extending the star and ring topology
2017-02-24 |  |  |  |  | changing the attributes of node to get better perforamance
2017-02-25 |  | Compiling the extended code
2017-02-26 |  |  | Extending the mesh and bus topology
2017-02-27
2017-02-28 |  |  |  | Analyze the routing table for number of iteration
2017-03-01
2017-03-02 | Initiating the node failure
2017-03-03 |  | Build the path
2017-03-04 |  |  | Show the network
2017-03-05
2017-03-06
2017-03-07 | Adding the additional functions to the code
2017-03-08
2017-03-09 |  | Compute topology | Generating the random IP address for each node
2017-03-10
2017-03-11
2017-03-12
2017-03-13 | Implementing Routing Optimization Algorithm
2017-03-14
2017-03-15
2017-03-16
2017-03-17
2017-03-18
2017-03-19 | Report Generation | Documentation | Presentation
2017-03-20
2017-03-21
2017-03-22
2017-03-23
2017-03-24
2017-03-25
2017-03-26
2017-03-27
2017-03-28
2017-03-29
2017-03-30
2017-03-31
2017-04-01